## Sheet1
Tasks | Start Date | Days To Complete
Proposal | 2019-09-01 | 9
Functional Description and ER Design | 2019-09-10 | 28
Database Design | 2019-10-08 | 28
Finalize Development Environment and Submit Report | 2019-11-05 | 17
Presentation and Demo | 2019-11-22 | 13